## Master Workplan
DATA QUALITY ASSESSMENT - MASTER WORK PLAN
Belize Health Information System (BHIS) ¦ Ministry of Health and Wellness
Project Period: January 19, 2026 - December 27, 2026 (50 weeks) ¦ Version 0.1
# | Phase / Activity | Responsible | Start Date | End Date | Deliverable | Due Date
P1 | PHASE 1: PREPARATION AND SCOPING (5 weeks: Jan 19 - Feb 22)
1.1 | Scoping and Methodology Development |  | Jan 19 | Feb 22
1.1.1 | Identify and map all relevant stakeholders | Infostructure Lead | Jan 19 | Jan 25
1.1.2 | Review and adapt WHO DQR methodology for Belize context | Infostructure Lead | Jan 26 | Feb 8
1.1.3 | Draft core indicators and priority health data areas | Infostructure Lead | Feb 2 | Feb 8 | Indicator Selection Matrix | Feb 8
1.1.4 | Alignment Sessions with key stakeholders (IDB, MOHW) | IL + DA + IDB + MOHW | Feb 2 | Feb 8
1.1.5 | Confirm facility list for site assessment (8-10 facilities) | IL + MOHW | Feb 2 | Feb 8
1.1.6 | Develop DQ Assessment Plan | Infostructure Lead | Feb 9 | Feb 22 | DQA Protocol | Feb 20
1.1.7 | Validation Session of DQA Methodology and Plan | IL + DL + MOHW | Feb 15 | Feb 22
1.3 | Data Requirements and Access |  | Feb 9 | Feb 22
1.3.1 | Document data extraction requirements from BHIS | IL + Data Analyst | Feb 9 | Feb 22 | Data Access Requirements | Feb 8
1.3.2 | Establish data access protocols and confidentiality agreements | IL + MOHW | Feb 15 | Feb 22
1.4 | IS4H Situation Analysis |  | Jan 19 | Feb 1
1.4.1 | Develop inventory of existing information products | IL + Data Analyst | Jan 19 | Feb 1
1.4.2 | Develop inventory of data tools and applications | IL + Data Analyst | Jan 19 | Feb 1
1.4.4 | Map the IT entity/unit (location, functions, reporting lines) | Data Analyst | Jan 19 | Feb 1 | IS4H Situation Analysis (Draft) | Feb 15
1.5 | Information Needs Assessment - Initial Scoping |  | Jan 26 | Feb 8
1.5.1 | Develop Information Needs Assessment questionnaire/interview guide | IL + Data Analyst | Jan 26 | Feb 8 | Info Needs Assessment Tool | Feb 8
1.5.2 | Identify key informants for information needs interviews | Infostructure Lead | Feb 2 | Feb 8
P2 | PHASE 2: DESK REVIEW (5 weeks: Feb 23 - Mar 29)
2.1 | Data Extraction and Preparation (1 week) |  | Feb 23 | Feb 29
2.1.1 | Extract core indicator data from BHIS for selected time period | BHIS IT | Feb 23 | Feb 29
2.1.2 | Prepare and adapt WHO desk review tool | IL + DA | Feb 23 | Feb 29
2.2 | Data Quality Four-Dimensions Desk Review (2 weeks) |  | Mar 1 | Mar 14
2.2.1 | Analyze data reporting completeness and data element completeness | IL + DA | Mar 1 | Mar 7
2.2.2 | Assess timeliness of reporting at various levels | IL + DA | Mar 1 | Mar 7
2.2.3 | Assess internal (logical, outliers) and temporal consistency | IL + DA | Mar 8 | Mar 14
2.2.4 | Assess external consistency by comparing with data sources | IL + DA | Mar 8 | Mar 14
2.4 | Health Data Workflow Mapping (1 week) |  | Feb 23 | Feb 29
2.4.4 | Document current standards adoption status (ICD-10, HL7) | IL + DA + IT | Feb 23 | Feb 29
2.4.5 | Assess CDEP readiness and document BHIS-CDEP data exchange requirements | IL + DA + IT | Feb 23 | Feb 29
2.5 | Reporting and Validation (2 weeks) |  | Mar 15 | Mar 29
2.5.1 | Compile Desk Review Report with baseline data quality scorecard | IL | Mar 15 | Mar 22 | Desk Review Report | Mar 29
2.5.3 | Present preliminary findings to MOHW stakeholders | IL + DA + DL | Mar 22 | Mar 29 | DQ Scorecard (Baseline) | Mar 29
2.5.4 | Finalize IS4H Situation Analysis Report | IL | Mar 22 | Mar 29 | IS4H Situation Analysis (Final) | Mar 29
P3 | PHASE 3: SITE ASSESSMENT (12 weeks: Mar 30 - Jun 14)
3.1 | Tool Development (2 weeks) |  | Mar 30 | Apr 12
3.1.1 | Develop data verification forms for priority indicators | IL | Mar 30 | Apr 5
3.1.2 | Create system assessment questionnaire | IL | Apr 6 | Apr 10
3.1.3 | Pilot test tools and finalize | IL | Apr 10 | Apr 12 | Site Assessment Tools | Apr 12
3.2 | Data Verification (4 weeks) |  | Apr 13 | May 10
3.2.1 | Notify selected facilities and coordinate visit logistics | IL + MOHW | Apr 13 | Apr 19
3.2.2 | Conduct site visits to Selected Facilities (incl. info needs interviews) | IL + DA | Apr 20 | May 3
3.2.3 | Calculate verification factors and compile data verification findings | IL | May 4 | May 10 | Data Verification Report | May 10
3.3 | System Assessment (4 weeks) |  | May 11 | Jun 7
3.3.1 | Analyze system assessment data from facility visits | IL | May 11 | May 24
3.3.2 | Conduct follow-up interviews with facility data managers | IL | May 25 | May 31
3.3.4 | Compile System Assessment Report | IL | Jun 1 | Jun 7 | System Assessment Report | Jun 7
3.4 | Information Needs Report Compilation |  | Jun 1 | Jun 14 | Info Needs Report (Draft) | Jun 7
P4 | PHASE 4: ANALYSIS AND PLANNING (16 weeks: Jun 15 - Oct 4)
4.1 | Comprehensive Data Analysis (4 weeks) |  | Jun 15 | Jul 12
4.2 | DQA Report Development (4 weeks) |  | Jul 13 | Aug 9
4.3 | DQIP Development (4 weeks) |  | Aug 10 | Sep 6 | Root Cause Analysis | Sep 6
4.4 | Stakeholder Consultations and Validation (3 weeks) |  | Sep 7 | Sep 27
4.5 | Report Finalization (1 week) |  | Sep 28 | Oct 4 | DQA Report; DQIP; Info Needs (Final) | Oct 4
P5 | PHASE 5: IMPLEMENTATION SUPPORT (13 weeks: Oct 5 - Dec 27)
5.1 | Standard Operating Procedures Development (4 weeks) |  | Oct 5 | Nov 1 | SOPs for DQ Assurance | Nov 1
5.2 | Monitoring and Evaluation Framework (3 weeks) |  | Nov 2 | Nov 22 | M&E Framework for DQ | Nov 22
5.3 | Data Quality Dashboard and Reporting Specifications (3 weeks) |  | Nov 23 | Dec 13 | Dashboard Specifications | Dec 13
5.5 | Data Quality Training Plan (2 weeks) |  | Dec 14 | Dec 27 | Training Materials; Closeout Report | Dec 27

## Gantt Chart (Weekly)
DQA WORK PLAN - WEEKLY GANTT CHART
Project Period: January 19, 2026 - December 27, 2026 (50 weeks)
[5 empty] | Jan |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
# | Phase / Activity | Type | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50
P1 | PHASE 1: PREPARATION AND SCOPING | Phase | Jan 19 | Feb 22
1.1.1 | Identify and map all relevant stakeholders | Activity | Jan 19 | Jan 25
1.1.2 | Review and adapt WHO DQR methodology | Activity | Jan 26 | Feb 08
1.1.3 | Draft core indicators and priority health data areas | Activity | Feb 02 | Feb 08
1.1.4 | Alignment Sessions with key stakeholders | Activity | Feb 02 | Feb 08
1.1.5 | Confirm facility list for site assessment | Activity | Feb 02 | Feb 08
1.1.6 | Develop DQ Assessment Plan | Activity | Feb 09 | Feb 22
1.1.7 | Validation Session of DQA Methodology and Plan | Activity | Feb 16 | Feb 22
1.3.1 | Document data extraction requirements from BHIS | Activity | Feb 09 | Feb 22
1.3.2 | Establish data access protocols | Activity | Feb 16 | Feb 22
1.4.1 | Develop inventory of information products | Activity | Jan 19 | Feb 01
1.4.2 | Develop inventory of data tools and applications | Activity | Jan 19 | Feb 01
1.4.4 | Map the IT entity/unit | Activity | Jan 19 | Feb 01
1.5.1 | Develop Information Needs Assessment questionnaire | Activity | Jan 26 | Feb 08
1.5.2 | Identify key informants for interviews | Activity | Feb 02 | Feb 08
M1 | [KEY MEETING: Steering Committee #1] | Meeting | Feb 02 | Feb 08
M2 | [KEY MEETING: Validation Session] | Meeting | Feb 16 | Feb 22
P2 | PHASE 2: DESK REVIEW | Phase | Feb 23 | Mar 29
2.1.1 | Extract core indicator data from BHIS | Activity | Feb 23 | Mar 01
2.1.2 | Prepare and adapt WHO desk review tool | Activity | Feb 23 | Mar 01
2.2.1 | Analyze data reporting completeness | Activity | Mar 02 | Mar 08
2.2.2 | Assess timeliness of reporting | Activity | Mar 02 | Mar 08
2.2.3 | Assess internal and temporal consistency | Activity | Mar 09 | Mar 15
2.2.4 | Assess external consistency | Activity | Mar 09 | Mar 15
2.4.4 | Document current standards adoption status | Activity | Feb 23 | Mar 01
2.4.5 | Assess CDEP readiness | Activity | Feb 23 | Mar 01
2.5.1 | Compile Desk Review Report | Activity | Mar 16 | Mar 22
2.5.3 | Present preliminary findings to MOHW | Activity | Mar 23 | Mar 29
2.5.4 | Finalize IS4H Situation Analysis Report | Activity | Mar 23 | Mar 29
M3 | [KEY MEETING: Desk Review Findings Presentation] | Meeting | Mar 23 | Mar 29
P3 | PHASE 3: SITE ASSESSMENT | Phase | Mar 30 | Jun 21
3.1.1 | Develop data verification forms | Activity | Mar 30 | Apr 12
3.1.2 | Create system assessment questionnaire | Activity | Apr 06 | Apr 12
3.1.3 | Pilot test tools and finalize | Activity | Apr 06 | Apr 12
3.2.1 | Notify facilities and coordinate logistics | Activity | Apr 13 | Apr 19
3.2.2 | Conduct site visits to Selected Facilities | Activity | Apr 20 | May 03
3.2.3 | Calculate verification factors | Activity | May 04 | May 10
3.3.1 | Analyze system assessment data | Activity | May 11 | May 24
3.3.2 | Follow-up interviews with facility data managers | Activity | May 25 | May 31
3.3.4 | Compile System Assessment Report | Activity | Jun 01 | Jun 07
M4 | [KEY MEETING: Site Visit Debriefs] | Meeting | May 04 | May 10
M5 | [KEY MEETING: Steering Committee #2] | Meeting | Jun 01 | Jun 07
P4 | PHASE 4: ANALYSIS AND PLANNING | Phase | Jun 15 | Oct 04
4.1 | Comprehensive Data Analysis | Activity | Jun 15 | Jul 12
4.2 | DQA Report Development | Activity | Jul 13 | Aug 09
4.3 | DQIP Development | Activity | Aug 10 | Sep 06
4.4 | Stakeholder Consultations and Validation | Activity | Sep 07 | Sep 27
4.5 | Report Finalization | Activity | Sep 28 | Oct 04
M6 | [KEY MEETING: DQIP Validation Workshop] | Meeting | Sep 14 | Sep 20
M7 | [KEY MEETING: Steering Committee #3] | Meeting | Sep 28 | Oct 04
P5 | PHASE 5: IMPLEMENTATION SUPPORT | Phase | Oct 05 | Jan 03
5.1 | Standard Operating Procedures Development | Activity | Oct 05 | Nov 01
5.2 | Monitoring and Evaluation Framework | Activity | Nov 02 | Nov 22
5.3 | Dashboard and Reporting Specifications | Activity | Nov 23 | Dec 13
5.5 | Data Quality Training Plan | Activity | Dec 14 | Jan 03
M8 | [KEY MEETING: Training Workshop] | Meeting | Dec 21 | Dec 27
M9 | [KEY MEETING: Project Closeout] | Meeting | Dec 28 | Jan 03
| [Add Meeting Here] | Meeting
| [Add Meeting Here] | Meeting
| [Add Meeting Here] | Meeting
| [Add Meeting Here] | Meeting
| [Add Meeting Here] | Meeting
LEGEND
Phase 1: Preparation and Scoping
Phase 2: Desk Review
Phase 3: Site Assessment
Phase 4: Analysis and Planning
Phase 5: Implementation Support
Key Meeting / Milestone
WEEK REFERENCE
W1 = Jan 19-25 | W10 = Mar 23-29 | W20 = May 25-31
W30 = Aug 3-9 | W40 = Oct 12-18 | W50 = Dec 21-27

## Deliverables Tracker
DQA DELIVERABLES TRACKER
# | Deliverable | Phase | Format | Due Date | Status
1.1 | Data Quality Assessment Protocol | Phase 1 | Document (Word) | Feb 20, 2026
1.2 | Data Quality Indicator Selection Matrix | Phase 1 | Spreadsheet (Excel) | Feb 8, 2026
1.3 | Data Access Requirements | Phase 1 | Document (Word) | Feb 8, 2026
1.4 | IS4H Situation Analysis Report (Draft) | Phase 1 | Report (Word) | Feb 15, 2026
1.5 | Information Needs Assessment Tool | Phase 1 | Questionnaire (Word) | Feb 8, 2026
2.1 | Desk Review Report | Phase 2 | Report (Word + Excel) | Mar 29, 2026
2.2 | Data Quality Scorecard (Baseline) | Phase 2 | Spreadsheet (Excel) | Mar 29, 2026
2.3 | IS4H Situation Analysis Report (Final) | Phase 2 | Report (Word + Diagrams) | Mar 29, 2026
3.1 | Site Assessment Tools | Phase 3 | Forms (Word/CSPro) | Apr 12, 2026
3.2 | Data Verification Report | Phase 3 | Report (Word + Excel) | May 10, 2026
3.3 | System Assessment Report | Phase 3 | Report (Word) | Jun 7, 2026
3.4 | Information Needs Assessment Report (Draft) | Phase 3 | Report (Word) | Jun 7, 2026
4.1 | Comprehensive DQA Report | Phase 4 | Report (Word + Annexes) | Oct 4, 2026
4.2 | Root Cause Analysis | Phase 4 | Document (Word) | Sep 6, 2026
4.3 | Data Quality Improvement Plan (DQIP) | Phase 4 | Plan (Word + Excel) | Oct 4, 2026
4.4 | Information Needs Assessment Report (Final) | Phase 4 | Report (Word) | Oct 4, 2026
5.1 | SOPs for Data Quality Assurance | Phase 5 | SOPs (Word) | Nov 1, 2026
5.2 | Training Materials Package | Phase 5 | Package (PPT + Word) | Dec 13, 2026
5.3 | M&E Framework for Data Quality | Phase 5 | Framework (Word) | Nov 22, 2026
5.4 | Dashboard Specifications | Phase 5 | Specifications (Word) | Dec 13, 2026
5.5 | Project Closeout Report | Phase 5 | Report (Word) | Dec 27, 2026